## Redmine
1. chia task dạng milestone, theo từng target version có deadline, tổng hợp dc các đầu task
2. Tạo các đầu task nhóm theo từng chức năng màn hình bao gồm:
tạo test spec
review
update review
dev
review code
update code
run test case
review
update evidence
3. tạo task: cần chú ý trạng thái, assign, due date
4. nội dung note ticket cần:
Hiện trạng chương trình
Vấn đề
Giải pháp
Cần confirm (xác nhận)

## Quy trình làm việc
đọc task -> note QA (review QA)-> yêu cầu dịch QA -> thực hiện task (cần note các bước làm trước - draft)

## chuẩn bị dự án mới
1/ Management
1.1 - Cấu trúc team, vai trò member
# Anxiety: Không rõ thể chế team, vai trò của các thành viên bên Nhật.
# Future: Có file mô tả thể chế team, từng member biết rõ cần phải liên lạc ai trong từng trường hợp cụ thể.
1.2 - Tool quản lý: Redmind...
# Anxiety: Không nhìn thấy tiến độ của phía Nhật và ngược lại.
# Future: Sử dụng tool quản lý Redmind chung cho cả 2 phía Nhật và Việt. Nếu giao task thì define luôn độ ưu tiên của task.
1.3 - Flow làm việc
# Anxiety: Flow làm việc chưa được định nghĩa.
# Future: Có buổi kickoff để cùng thống nhất với nhau về flow làm việc, tool quản lý, quản lý Q&A, các phase từng giai đoạn, môi trường phát dev, thành viên dự án
2/ Communication
# Anxiety: Chưa thống nhất phương thức trao đổi khi cần liên lạc hoặc Q&A.
# Future: Thống nhất được sử dụng các phương thức trao đổi bên dưới.
+ Meeting: Daily, weekly, monthly
+ Chatwork
+ Call trực tiếp: Skype
+ Tạo file Q&A chung, có template rõ ràng, các vấn đề đã trao đổi được lưu lại đầy đủ trong file Q&A.
3/ Development
3.1 - Nghiệp vụ
# Anxiety: không nhìn thấy bức tranh toàn thể hệ thống, không rõ nghiệp vụ của dự án, implement dựa trên spec nhưng spec lại không rõ ràng
# Future: Có buổi giải thích tổng quan về nghiệp vụ dự án, giải thích tổng quan theo từng module nếu có thể. Có những buổi giải thích về spec (cách đọc hiểu) trước khi implement.
1. nên có buổi giải thích tổng quan về nghiệp vụ dự án ( thường sau buổi kickoff )
2. giải thích về spec ( cách đọc hiểu )
3. nếu có thể mong muốn giải thích tổng quan theo từng module
3.2 - Quản lý source code
# Anxiety: Chưa thống nhất tool quản lý, chưa chia branch và vai trò quyền hạn của người create, review, merge source code. Chưa thống nhất cách comment, cách pull/push code.
# Future: Thống nhất tool quản lý là Git, source được chia branch cụ thể và có rule vận hành.
3.3 - Môi trường
# Anxiety: chưa chuẩn bị môi trường để dev, test, deploy.
# Future: dev, test có thể thực hiện được ở local server. Có server AWS access được từ cả 2 phía để tiện triển khai và confirm.
3.4 - Công nghệ
# Anxiety: Không nắm được công nghệ sử dụng trong dự án.
# Future: Có thời gian nghiên cứu, training về công nghệ sử dụng trong dự án.
3.5 - Dev
# Anxiety: Nếu là dự án maintain, mất thời gian tìm hiểu source code cũ.
# Future: Có tài liệu coding convention, có tài liệu checklist, lỗi common. Có thời gian tìm hiểu source code cũ.
ngoài ra cần có buổi kickoff để cùng thống nhất với nhau về quy trình làm dự án
như là tool quản lý, quản lý Q&A, các phase từng giai đoạn
môi trường phát dev, thành viên dự án
3.6 - Test
# Anxiety: Khi test tích hợp, member việt nam chưa có nhiều kinh nghiệm test các case abnormal.
# Future: Có ví dụ về các case abnormal thường xảy ra (common) và cách test các case đó.
3.7 - Deploy
# Anxiety: member VN chưa có kinh nghiệm deploy sử dụng các tool CI/CD.
# Future: thành thạo CI / CD
Input (design) lởm + CR nhiều trong lúc dev.
Phần này a thấy nên bổ sung thêm là thống nhất quan điểm test từ đầu: là unit test hay test tích hợp hay system test thì sẽ có những ví dụ hoặc check list tương ứng
Ví dụ: nếu là unit test thì có thể có checklist lỗi common giống như bên mục của #dev
còn nếu là test tích hợp, system test thì cần phải có file quan điểm test bên Nhật đưa về giống như bên JIMOS

## Tạo thói quen
1. Buổi sáng:
list ra công việc cần làm trong ngày bao gồm việc công ty cá nhân: 15 phút
Tổng hợp các đầu việc redmine, đánh giá tiến độ, ai quản lý, tình trạng, độ ưu tiên, due date
2. Buổi chiều:
đánh giá các đầu việc đã làm hôm nay: 30 phút
note tiến độ cho từng công việc, tình trạng
3. tư duy code
đọc spec tới đâu note QA tới đấy
tìm hiểu code common, đã dùng
nghĩ ra các test case,unit test có thể xảy ra, cận biên
draft code theo từng block
4. tư duy quản lý
xem plan dự án
bàn giao những gì
đang gặp vấn đề gì
action cho các vấn đề đó (cần list ra nhiều cách giải quyết - chọn cách giải quyết tối ưu)
5. Trước 1 vấn đề cần xoay quanh, đánh giá vấn đề, đưa ra các giải pháp rồi lọc bỏ dần
6. Tạo task:
Theo các đầu task to như các màn hình, module rồi break ra các task nhỏ liên quan
Viết prefix là tên người assign, tên chức năng
vd: [TrungLV][Login] - đọc spec
Xoay quanh các vấn đề, đưa ra các câu hỏi đúng trọng tâm
7. Confirm 1 vấn đề:

## Cach giai quyet van de
Trước 1 dự án mới
List hết tất cả các công việc phải làm, càng nhiều càng tốt, các khả năng có thể xảy ra
Đánh giá độ ưu tiên
Hỏi ý kiến team thống nhất ra các task và độ ưu tiên
Trao đổi với KH để thêm bớt các đầu task
output: list task
list ra tất cả các câu hỏi -> đưa ra action
đưa các task lên redmine
cách communicate
SDS: | summary
detail
summary
PREP | point
reason
example
point

## JIMOS
Prefix API/Batch:
| ký tự 1 | Ký tự 2 | Ký tự 3
| C | C | R | 94
| C: Order customer (受注・顧客) | Client | Create/Update/Delete/Modify
B: batch
G: 債権 - liên quan đến tiền
E : Button 3 (債権 - Xuất nhập hàng)
D : 発注 B : 企画・プロモーション F : 在庫
Combobox có 5 loại hiện tại 3 hãng sản phẩm mà jimos đang bán:
Có 5 mode order:
|  | Normal Order |  |  | 通常注文
|  | Edit normal Order |  |  | 注文修正
|  | Cyrcle Order |  |  | 定期申込
|  | Edit Cyrcle Order - Master |  |  | 定期マスタ修正
|  | Edit Cyrcle Order - CM |  |  | 定期予定修正
Note meeting review source code
. Mục đích review
- Chia sẻ spec GB0090 cho các member khác hiểu để có thể backup được trong mọi trường hợp
- Nội dung GB0090:
GB0090: xuất hóa đơn và yêu cầu đòi tiền từ sony payment
Các bước chạy batch:
- đăng ký đơn thông thường
- xuất kho gấp
- chay batch confirm xuất hàng: EB0081
- chạy batch GB0021 cập nhật doanh thu
- chạy GB0090 yêu cầu đòi tiền
Thanh toán đen: Khách hàng trả tiền cho JIMOS thông qua sony payment
Thanh toán đỏ: khách hàng đổi/trả hàng thì JIMOS sẽ hoàn tiền cho khách hàng
GB0090: TT đen - smart
GB0093: Smart: TT đen => TT đỏ
GB0094: Direct: TT đen => TT đỏ
Memo nội dung review code:
1. nội dung comment đang viết tiếng việt => cần chuyển sang tiếng anh
2. cần refactor lại code: xóa comment, khai báo thừa biến
3. cho constant phần header, footer xuất file
sẽ review thêm về logic code, dto
TT_MIG_JYOTO_DATA.BLCOT_KBN 「2： Đen」
カード会社返金が選べるパターン
①Directオーソリで、Directに黒伝譲渡されている
②Smartオーソリで、Smartに黒伝譲渡されている
①のパターン
プロセスIDがない、移行用譲渡データにレコードが無い
②のパターン
プロセスIDが有る
※プロセスIDがなく、移行用譲渡データにレコードが有るパターンのみ
カード会社返金選べない
2018-07-18 15:50
A：Directオーソリ Direct黒伝
B： Smart黒伝
C：Smartオーソリ Direct黒伝
D： Smart黒伝
15:55
Trả lời
Trích dẫn
Công việc
Đường dẫn
A
15:55
プロセスID× 移行用譲渡データ×
15:56
B
プロセスID× 移行用譲渡データ〇
⇒GB0094で譲渡
15:56
C is impossible
15:57
D
プロセスID〇 移行用譲渡データ×
⇒GB0090でfile output
Trạng thái việc hoàn trả đơn hàng
public static LocalDB.MasterSyncDBDataSet.TM_HNKN_HOHORow 郵便振込 { get { return Instance.FindByCodeValue("01"); } }
public static LocalDB.MasterSyncDBDataSet.TM_HNKN_HOHORow 銀行振込 { get { return Instance.FindByCodeValue("02"); } }
public static LocalDB.MasterSyncDBDataSet.TM_HNKN_HOHORow 現金書留 { get { return Instance.FindByCodeValue("03"); } }
public static LocalDB.MasterSyncDBDataSet.TM_HNKN_HOHORow 即時返金 { get { return Instance.FindByCodeValue("04"); } }
public static LocalDB.MasterSyncDBDataSet.TM_HNKN_HOHORow 雑収入 { get { return Instance.FindByCodeValue("06"); } }
public static LocalDB.MasterSyncDBDataSet.TM_HNKN_HOHORow 調整 { get { return Instance.FindByCodeValue("07"); } }
public static LocalDB.MasterSyncDBDataSet.TM_HNKN_HOHORow ポイント { get { return Instance.FindByCodeValue("09"); } }
Các phương thức thanh toán
public static LocalDB.MasterSyncDBDataSet.TM_SHRAI_HOHORow クレジットカード { get { return Instance.FindByCodeValue("1"); } }
public static LocalDB.MasterSyncDBDataSet.TM_SHRAI_HOHORow 代金引換 { get { return Instance.FindByCodeValue("2"); } }
public static LocalDB.MasterSyncDBDataSet.TM_SHRAI_HOHORow 郵便_コンビニ_モバイル { get { return Instance.FindByCodeValue("3"); } }
public static LocalDB.MasterSyncDBDataSet.TM_SHRAI_HOHORow 口座振替 { get { return Instance.FindByCodeValue("4"); } }
public static LocalDB.MasterSyncDBDataSet.TM_SHRAI_HOHORow 給与天引き { get { return Instance.FindByCodeValue("5"); } }
public static LocalDB.MasterSyncDBDataSet.TM_SHRAI_HOHORow 店舗その他 { get { return Instance.FindByCodeValue("6"); } }
Trạng thái đơn hàng:
KB0258応対ステータス区分
select * from TM_OTAI_SYRI_KBN;
-- don hang thanh cong + cac phuong thuc thanh toan khac nhau
select tjh.*, kssk.SYKKA_DTE from tt_jty_hdr tjh inner join tt_kkyak_shrai_hoho ho on ho.kkyak_shrai_hoho_id = tjh.kkyak_shrai_hoho_id and ho.shrai_hoho_kbn = '5'
inner join TT_KKYAK_SYKKA_SKN_KNRI kssk on kssk.KAIIN_NBR = tjh.KAIIN_NBR and kssk.JTY_NBR = tjh.JTY_NBR
where
exists ( select 1 from tt_jty_msai tjm where tjm.kaiin_nbr = tjh.kaiin_nbr and tjh.jty_nbr = tjm.jty_nbr and tjm.jty_msai_hyoji_sts_kbn = '09')
--and
--tjh.KAIIN_NBR = 12012395 and tjh.JTY_NBR = 13
order by kssk.SYKKA_DTE desc;
Trạng thái đơn hàng cụ thể
select a.JTY_MSAI_HYOJI_STS_KBN from TT_JTY_MSAI a where a.KAIIN_NBR = 12012376 and a.JTY_NBR = 8;
| Số lần thanh toán |  | 一括
| KB0229カード支払区分() |  | 分割2回
リボ
ボーナス一括
public KB0213受注明細ステータス区分() {
CodeItem[] codeItems = new CommonCodeItem[7];
codeItems[0] = new CommonCodeItem("1", "未確定", "未確定", 1, true, null, null, new Object[]{});
codeItems[1] = new CommonCodeItem("2", "受確", "受確", 2, true, null, null, new Object[]{});
codeItems[2] = new CommonCodeItem("3", "取消", "取消", 3, true, null, null, new Object[]{});
codeItems[3] = new CommonCodeItem("4", "指示", "指示", 4, true, null, null, new Object[]{});
codeItems[4] = new CommonCodeItem("5", "出確", "出確", 5, true, null, null, new Object[]{});
codeItems[5] = new CommonCodeItem("6", "売上", "売上", 6, true, null, null, new Object[]{});
codeItems[6] = new CommonCodeItem("7", "変更", "変更", 7, true, null, null, new Object[]{});
this.refreshCodeItems(codeItems);
}
Màn hình thể hiện đơn hàng màu đỏ là trả hàng
| TT_KKYAK_SYKKA_SKN_KNRI.SYKKA_DTE |  |  | Ngày xuất hàng
select * from tt_jty_hdr tjh
inner join tt_kkyak_shrai_hoho ho on ho.KKYAK_SHRAI_HOHO_ID = tjh.KKYAK_SHRAI_HOHO_ID and ho.SHRAI_HOHO_KBN = '1' --カード
inner join TT_KKYAK_SYKKA_SKN_KNRI kssk on kssk.KAIIN_NBR = tjh.KAIIN_NBR and kssk.JTY_NBR = tjh.JTY_NBR
where (tjh.KAIIN_NBR,tjh.JTY_NBR) in (
select tjm1.KAIIN_NBR,tjm1.JTY_NBR from tt_jty_msai tjm1
inner join tt_jty_msai tjm2 on tjm1.KAIIN_NBR = tjm2.KAIIN_NBR and tjm1.JTY_NBR = tjm2.JTY_NBR and tjm1.JTY_MSAI_NBR <> tjm2.JTY_MSAI_NBR and tjm2.JTY_MSAI_HYOJI_STS_KBN = '09' and tjm2.HNPIN_STS_KBN is null and tjm1.SYKKA_JI_SYKKA_NBR = tjm2.SYKKA_JI_SYKKA_NBR
inner join tt_jty_msai tjm3 on tjm1.KAIIN_NBR = tjm3.kaiin_nbr and tjm1.JTY_NBR = tjm3.jty_nbr and tjm3.JTY_MSAI_NBR <> tjm2.JTY_MSAI_NBR and tjm3.JTY_MSAI_NBR <> tjm1.JTY_MSAI_NBR and tjm2.JTY_MSAI_HYOJI_STS_KBN = '09' and tjm3.HNPIN_STS_KBN is null and tjm2.SYKKA_JI_SYKKA_NBR = tjm3.SYKKA_JI_SYKKA_NBR
where tjm1.HNPIN_STS_KBN = '4'
and tjm1.JTY_MSAI_HYOJI_STS_KBN = '09'
);
CCR088
Lưu ý:
| TT_KKYAK_SYKKA_SKN_KNRI | Customer shipment receivables management |  |  |  |  | Quản lý các khoản phải thu khách hàng
| TT_SYKKA_BTU_RYO_HSI_KNRI | Shipment by using generation management |  |  |  |  | Lô hàng bằng cách sử dụng quản lý thế hệ
| JTY_MSAI_HYOJI_STS_KBN | Code: status hiển thị chi tiết hóa đơn
| HNPIN_STS_KBN | Code: Status trả hàng
| SYKKA_JI_SYKKA_NBR | Mã xuất kho khi xuất kho
| AZUKARKN_RYO | Deposits use |  | Tiền gửi sử dụng
| RKI_URAGE_GAK | Total sales amount
| TT_SKN_URAGE_RIREKI | 債権売上履歴 |  | Lịch sử bán hàng phải thu
ttSknUrageRirekiDao
Các bước run batch GB0093
1. 通常受注作成
2. 緊急出荷（EB9901
xong update TT_SYKKA_HDR
3. 出荷確定（GB0021）
4. 完了（GB0090）
5. 画面で返品依頼（CC0075⇒CC0078⇒CC0079）
6. 返品確定（GB0030）- 返品の場合だけ
バッチを実行する前に
返品依頼ヘッダ．返品依頼ステータス＝30、返品依頼明細．返品依頼明細ステータス＝30
TT_HNPIN_IRAI_HDR.HNPIN_IRAI_STS_KBN
TT_HNPIN_IRAI_MSAI.HNPIN_IRAI_MSAI_STS_KBN
にすることを忘れないこと。
where kaiin_nbr & jty_nbr
7. GC0043
8. GB0041実行
1.Lay thong tin lich tra no tu bang nay | TT_HNKN_YOTE | Repayment schedule |  |  |  | Dự định trả hàng
| TT_JYOTO_NYKN_ZNGK_KNRI | Transfer payment balance management |  |  |  | Chuyển khoản quản lý số dư thanh toán
| JYOTO_NYKN_ZNGK | Transfer payment balance |  |  |  | Số dư còn lại để chuyển khoản |  |  |  | 6107
2. Bang luu thong tin tien trong tk cua khach hang | TT_JYOTO_NYKN_ZNGK_KNRI | bảng lưu số dư còn lại của khách hàng cần chuyển khoản
[8 empty] | so tien hoan | HnknGak | 432
| TT_CARD_SKN_JYOTO_HDR | Bảng chuyển khoản thẻ cho vay
| HnknHohoKbn | // 返金方法＝"13：カード会社返金" | [5 empty] | refund method = "13: hoàn lại tiền của công ty thẻ"
3. Bang Chuyển giao lại lịch sử thay đổi quản lý số dư còn lại: insert bản ghi mới và update thêm tiền | TT_JYOTO_NYKN_ZNGK_KNRI_HNKO | Bang Chuyển giao lại lịch sử thay đổi quản lý số dư còn lại
5675
| TT_JYOTO_NYKN_ZNGK_KNRI_HNKO | JYOTO_NYKN_ZNGK |  | lưu số tiền còn lại
5032
4. Bảng chuyển khoản thẻ cho vay | TT_CARD_SKN_JYOTO_HDR | [8 empty] | 3000
Trạng thái của việc trả hàng
| HNPIN_IRAI_STS_KBN | TT_HNPIN_IRAI_HDR |  |  | Return request header - header yêu cầu trả hàng
| 10 | 返品依頼: yêu cầu trả hàng
| 30 | 受取確定 | Xác nhận trả hàng
| 90 | 返品確定 | Hoàn tất trả hàng
Lưu ý: CCM021, CCR088
| kkyakSykkaSknKnri.getRkiUrikakeGak() |  | 9775
| kkyakSykkaSknKnri.getRkiHnpinZmiGak() |  | 9064
| ttHnpinIraiHdr.getHnpinIraiGak() |  | 1575
| kkyakSykkaSknKnri.getRkiNbkiGak() |  | 0
| TT_SKN_URIKAKE_KESIKM_RIREKI |  | Đăng ký dữ liệu lịch sử cho vay trả lại hàng hóa
Config tool EscottTool chạy trên local máy dev
有効性チIック | đánh giá hiệu quả
カード番号 | card number
名_人 | card name
有効期限 | expiration date
支忆回数 | Số lần thanh toán
支忆額 | Tiền
会頁番号 | number page
事案部コード | case code
受注番号 | order number
オーソリ管理番号 | authorization number
才ーソリ結果コード | talisman result code
Trạng thái của các đơn hàng | KB0212
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 受残 { get { return Instance.FindByCodeValue("01"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 予約 { get { return Instance.FindByCodeValue("02"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 引当 { get { return Instance.FindByCodeValue("03"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 変更 { get { return Instance.FindByCodeValue("04"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 出依 { get { return Instance.FindByCodeValue("05"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 出確 { get { return Instance.FindByCodeValue("06"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 売上 { get { return Instance.FindByCodeValue("07"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 入金 { get { return Instance.FindByCodeValue("08"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 完了 { get { return Instance.FindByCodeValue("09"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 取消 { get { return Instance.FindByCodeValue("10"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 督１ { get { return Instance.FindByCodeValue("11"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 督２ { get { return Instance.FindByCodeValue("12"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 督３ { get { return Instance.FindByCodeValue("13"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 委託 { get { return Instance.FindByCodeValue("14"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 倒１ { get { return Instance.FindByCodeValue("15"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 倒２ { get { return Instance.FindByCodeValue("16"); } }
public static LocalDB.MasterSyncDBDataSet.TM_JTY_MSAI_HYOJI_STSRow 倒３ { get { return Instance.FindByCodeValue("17"); } }
1) | GB0021: Cập nhật doanh thu
Điều kiện thực hiên:
Có đơn hàng đã được xác nhận
|  | 1) | Tạo đơn hàng thông thường (Hoặc đơn hàng tạo ra từ kế hoạch gửi định kì Qua batch CB0120)
|  | 2) | Thực hiện xuất kho nhanh */ Xem sheet Chạy batch từ unimo
|  | 3) | sửa Header Xuất kho.Ngày xác nhận xuất kho = not null
TT_SYKKA_HDR.SYKKA_KAKTE_DTE = not null
|  |  | Header Xuất kho.Flag xác nhận xuất kho = 1 | [5 empty] | select a.SYKKA_KAKTE_DTE, a.SYKKA_KAKTE_FLG, a.JTY_NBR from proc.TT_SYKKA_HDR a
|  |  | TT_SYKKA_HDR.SYKKA_KAKTE_FLG = 1 | [5 empty] | where a.KAIIN_NBR = '12009564'
|  |  | * Thao tác trên gọi chung là xác nhận đơn hàng | [5 empty] | --and a.JTY_NBR = '3'
--update proc.TT_SYKKA_HDR a
|  | Phương pháp thực hiện | [6 empty] | --set a.SYKKA_KAKTE_DTE = '2016/06/14',
|  |  | Gọi lệnh $ ./GB0021 | [5 empty] | -- a.SYKKA_KAKTE_FLG = '1'
|  | Điều kiện sau khi thực hiện: | [6 empty] | --where a.KAIIN_NBR = '12009564'
Có thể thực hiện trả hàng
GB0090 Tạo dữ liệu liên quan đến thẻ chuyển cho sony payment
Chạy các bước trên sau đó chạy ./GB0090
C
G
B
D
E
select a.SYKKA_KAKTE_DTE, a.SYKKA_KAKTE_FLG, a.JTY_NBR from proc.TT_SYKKA_HDR a
where a.KAIIN_NBR = '12009564'
--and a.JTY_NBR = '3'
--update proc.TT_SYKKA_HDR a
--set a.SYKKA_KAKTE_DTE = '2016/06/14',
-- a.SYKKA_KAKTE_FLG = '1'
--where a.KAIIN_NBR = '12009564'
--and a.JTY_NBR = '3'xác nhận đơn hàng

## SQL
select * from TM_SMART_KAIIN_KNRI where KAIIN_ID = 'B12018041900002';
select * from tm_cde where cde_id = 'KB0229';
select * from TM_MDLE_KNRI where mdle_id in ('CB0090','GB0094');
select BLCOT_KBN from TT_MIG_JYOTO_DATA;
select * from TT_MIG_JYOTO_DATA;
select * from SY_MNSI_DTE_TBL;
update TM_MDLE_KNRI set otpt_saki_dir_path = null where mdle_id='';
select * from TT_DALY_AUTHRI_MI_SYONIN_HDR;++
select * from TM_BTH_KIDOU_PRM where MDLE_ID = 'CB0092';
select KAIIN_ID from TT_AUTHRI_KNRI where KAIIN_NBR = '12012075' and AUTHRI_KNRI_NBR = 5965;
select * from TM_BTH_JKO_JOKYO_KNRI
#NAME?
order by SIJI_DTM desc;
select * from TM_SMART_KAIIN_KNRI where kaiin_nbr='12012275' order by SS_TRKU_DTM desc;
update TM_BTH_JKO_JOKYO_KNRI set syri_zmi_kensu = 2000 where syri_jko_seq = 210575;
select RYO_YOTE_PNT ,AZUKARKN_RYO_YOTE_GAK, JTY_SORYO_ZEKMI, RYO_PNT, AZUKARKN_RYO_YOTE_GAK from TT_JTY_HDR_KARI_TRKU where KAIIN_NBR = '12012275';
JtySoryo = 0;
select * from TM_KKYAK where KAIIN_NBR = '12012315';
select * from TT_OUTSOURCER_KAIIN_ID_KNRI;
update TM_SMART_KAIIN_KNRI set card_nbr_msk = '1234********5435' where KAIIN_ID='UN1201207500011';
select * from TT_OUTSOURCER_KAIIN_ID_KNRI where KAIIN_ID = 'B12018041900003';
SELECT TM_SYS_CMMN.CARD_KSYA_HNKN_SITEI_KNO_DTE FROM TM_SYS_CMMN;
select * from TM_SMART_RESPONSE where RESPONSE_CDE = 'K01';
select * from TT_AUTHRI_KNRI where KAIIN_ID='UN1201207500011' and TRKSI_FLG = 1;
select TRKSI_FLG from TT_AUTHRI_KNRI where KAIIN_ID='UN1201207500010';
update TT_AUTHRI_KNRI set card_nbr = '1234********5435' where KAIIN_ID='UN1201207500011';
commit;
update TM_BTH_JKO_JOKYO_KNRI set SYRI_JOKYO = 3 where MDLE_ID <> 'CB0091' and SYRI_JOKYO = 2;
commit;
select a.SYKKA_KAKTE_DTE, a.SYKKA_KAKTE_FLG, a.JTY_NBR from proc.TT_SYKKA_HDR a
where a.KAIIN_NBR = '12012255'
and a.JTY_NBR = '2';
update proc.TT_SYKKA_HDR a
set a.SYKKA_KAKTE_DTE = '2018/05/14',
a.SYKKA_KAKTE_FLG = '1'
where a.KAIIN_NBR = '12012255'
and a.JTY_NBR = '2';
commit;
select * from TT_AUTHRI_KNRI where KAIIN_NBR = '12012255';
select * from TT_AUTHRI_KNRI where KAIIN_NBR = '12012219';
select * from TT_AUTHRI_KNRI where KAIIN_NBR = '12012075';
card_Shrai_Kbn
select T1_.KKYAK_JSY_ID as C1_, T1_.KAIIN_NBR as C2_, T1_.KKYAK_JSY_KBN as C3_, T1_.KYAK_KANJI_NME as C4_, T1_.KYAK_SEI_KN_NME as C5_, T1_.KYAK_NME_KN_NME as C6_, T1_.YBIN_NBR as C7_, T1_.JSY_CDE as C8_, T1_.JSY_TODOFUKN_CDE as C9_, T1_.BANCHI as C10_, T1_.TATMN_NME as C11_, T1_.TEL_NBR as C12_, T1_.CUSTOMER_BRCD as C13_, T1_.SAISIN_KKYAK_JSY_ID as C14_, T1_.MUKO_FLG as C15_, T1_.SS_TRKU_SYA_CDE as C16_, T1_.SS_TRKU_DTM as C17_, T1_.SS_TRKU_SYS as C18_, T1_.SS_TRKU_MDLE as C19_, T1_.SS_KOSIN_SYA_CDE as C20_, T1_.SS_KOSIN_DTM as C21_, T1_.SS_KOSIN_SYS as C22_, T1_.SS_KOSIN_MDLE as C23_, T1_.SS_MNSI_DTE as C24_, T1_.SS_KAITEI_NBR as C25_, T1_.SS_KOSINMT_IP_ADDR as C26_, T1_.SS_SAKUJO_FLG as C27_ from TT_KKYAK_JSY T1_ where (T1_.KKYAK_JSY_ID = 15622);
select * from TM_HAISO_KSYA_HAISO_HOHO_KBN where HAISO_KSYA_CDE = 3;
select * from TT_KKYAK_HAISO_HOHO where kaiin_nbr='12012255';
select * from TT_SHN_SRCH where SHN_ID = '002089' and SHN_ATTR_ID = '00' and SHN_SRCH_SBT_KBN = '1' and SS_SAKUJO_FLG = '0';
SELECT --CCR042_04
NVL(SUM(RKI_CNT), 0) AS RKI_CNT
FROM
TT_JGB_BTU_KKYAK_KODO_KNRI;
select * from TM_SMART_KAIIN_KNRI where KAIIN_NBR = '12012275' and KAIIN_ID = 'UN1201207500446';
--delete TM_SMART_KAIIN_KNRI where KAIIN_NBR = '12012275' and kaiin_ID in( 'UN1201227500002','UN1201227500003', 'UN1201227500004');
--commit;
select * from TT_AUTHRI_KNRI where KAIIN_NBR = '12012275';
select * from TM_TEIKI_HDR where KAIIN_NBR = '12012275' and teiki_mst_nbr = 8;
select * from TM_TEIKI_MSAI where kaiin_nbr = '12012275' and teiki_mst_nbr = 8;
select x.* from TT_JTY_HDR x where x.kaiin_nbr = '12012275' and jty_nbr = 242;
select DISTINCT b.KKYAK_SHRAI_HOHO_ID_ERR, b.* from TT_JTY_HDR_KARI_TRKU b where b.kaiin_nbr = '12012275' and b.KKYAK_SHRAI_HOHO_ID_ERR is not null order by b.SS_KOSIN_DTM desc;
order by jty_nbr desc;
-- and jty_nbr = 232;
select * from TT_JTY_MSAI where kaiin_nbr = '12012275' and jty_nbr = 232;
select RYO_YOTE_PNT,AZUKARKN_RYO_YOTE_GAK, JTY_ZEKMI_AMT, JTY_SORYO_ZEKMI, RYO_PNT from TT_JTY_HDR_KARI_TRKU where KAIIN_NBR = '12012275';
select g.* from TT_TEIKI_MST_HDR_KR_TRKU g where g.KKYAK_SHRAI_HOHO_ID_ERR = 74;
select b.* from TT_JTY_HDR_KARI_TRKU b where
b.kaiin_nbr = '12012275' and
b.KKYAK_SHRAI_HOHO_ID_ERR = 74;
select * from TT_KKYAK_SHRAI_HOHO;
0
select x.PROCESS_ID, x.process_pwd,x.* from TT_AUTHRI_KNRI x where x.KAIIN_NBR = '12012075' order by ss_kosin_dtm desc;
select * from TM_SMART_KAIIN_KNRI where KAIIN_NBR = '12012262';
--and kaiin_id='UN1201226200001';
select * from TT_KKYAK_SHRAI_HOHO where KAIIN_NBR = '12012415' and CARD_SHRAI_KBN = '21';
select * from TM_TEIKI_HDR where KAIIN_NBR = '12012262';
select x.JIKAI_TDK_KIBO_DTE, x.* from TM_TEIKI_MSAI x where KAIIN_NBR = '12012415';
select x.SYKKA_HORY_RYU_KBN ,x.* from TT_JTY_HDR x where x.kaiin_nbr = '12012415' and jty_nbr = 5;
select a.SYKKA_KAKTE_DTE, a.SYKKA_KAKTE_FLG, a.JTY_NBR from proc.TT_SYKKA_HDR a
where a.KAIIN_NBR = '12012475';
and a.JTY_NBR = '3';
update proc.TT_SYKKA_HDR a
set a.SYKKA_KAKTE_DTE = '2018/05/29',
a.SYKKA_KAKTE_FLG = '1'
where a.KAIIN_NBR = '12012475' and a.JTY_NBR = '3';
commit;
select * from TM_BTH_JKO_JOKYO_KNRI --where MDLE_ID = 'CB0091'
order by SIJI_DTM desc;
select * from TT_SYKKA_HDR where KAIIN_NBR = '12012435';
select * from TT_AUTHRI_KNRI where KAIIN_NBR = '12012435' and AUTHRI_KNRI_NBR = 6280;
select * from TM_SMART_KAIIN_KNRI where KAIIN_ID = 'UN1201243500001';
--update TM_SMART_KAIIN_KNRI set KAIIN_ID_STS = 1 where KAIIN_ID = 'UN1201243500001';
--commit;
update TM_BTH_JKO_JOKYO_KNRI set SYRI_JOKYO = 3 where MDLE_ID <> 'EB9901';
commit;
select TM_SYS_CMMN.KEIRI_TEKIYO_YM, TM_SYS_CMMN.* from TM_SYS_CMMN;
update TM_SYS_CMMN set TM_SYS_CMMN.KEIRI_TEKIYO_YM = '201808' where key_val = 1;
commit;
select * from TM_SMART_KAIIN_KNRI where KAIIN_ID = 'UN1201191500016';
select * from TT_AUTHRI_KNRI where KAIIN_nbr = '12009402'
and jty_nbr='158'
order by ss_kosin_dtm desc;
select * from TT_JTY_HDR where KAIIN_nbr = '12009402' and jty_nbr=
update TM_SMART_KAIIN_KNRI set kaiin_id_sts = 1 where KAIIN_ID = 'UN1201191500022';
commit;
select * from TM_SMART_KAIIN_KNRI where KAIIN_NBR = '12011915';
12012475
select * from TT_KKYAK_SHRAI_HOHO T1_ where (T1_.KAIIN_NBR = '12012475');
select * from TT_JTY_MSAI;
select * from TT_DALY_AUTHRI_MI_SYONIN_MSAI;
select * from TT_JTY_HDR where KAIIN_NBR = '12012495';
select * from TT_DALY_AUTHRI_MI_SYONIN_HDR;
select * from TT_SYKKA_HDR where KAIIN_NBR = '12012495';
select * from TT_AUTHRI_KNRI where KAIIN_ID = 'UN1201191500016' order by ss_kosin_dtm desc;
update TT_AUTHRI_KNRI set TRHIKI_SIKIBETU_NBR = '123456' where KAIIN_ID = 'UN1201191500016';
commit;
6339
select * from TT_MKR_HNPIN_SIJI_HDR;
select * from TT_MIG_JYOTO_DA;
select * from tt_jty_msai tjm inner join tt_jty_hdr tjh on tjh.KAIIN_NBR = tjm.KAIIN_NBR and tjh.JTY_NBR = tjm.JTY_NBR
inner join tt_kkyak_shrai_hoho ho on ho.kkyak_shrai_hoho_id = tjh.KKYAK_SHRAI_HOHO_ID and ho.shrai_hoho_kbn = '3'
left outer join tt_hnpin_irai_hdr hnpin on hnpin.kaiin_nbr = tjh.KAIIN_NBR and hnpin.jty_nbr = tjh.JTY_NBR
where tjm.JTY_MSAI_HYOJI_STS_KBN = '07' and hnpin.kaiin_nbr is null;
select tjh.*,kssk.SYKKA_DTE from tt_jty_hdr tjh inner join tt_kkyak_shrai_hoho ho on ho.kkyak_shrai_hoho_id = tjh.kkyak_shrai_hoho_id and ho.shrai_hoho_kbn = '1'
inner join TT_KKYAK_SYKKA_SKN_KNRI kssk on kssk.KAIIN_NBR = tjh.KAIIN_NBR and kssk.JTY_NBR = tjh.JTY_NBR
where
exists ( select 1 from tt_jty_msai tjm where tjm.kaiin_nbr = tjh.kaiin_nbr and tjh.jty_nbr = tjm.jty_nbr and tjm.jty_msai_hyoji_sts_kbn = '09')
and tjh.KAIIN_NBR = 12012395
order by kssk.SYKKA_DTE desc;
--order by kssk.SYKKA_DTE desc;
select tjh.* from tt_jty_hdr tjh inner join tt_kkyak_shrai_hoho ho on ho.kkyak_shrai_hoho_id = tjh.kkyak_shrai_hoho_id and ho.shrai_hoho_kbn = '1'
where
exists ( select 1 from tt_jty_msai tjm where tjm.kaiin_nbr = tjh.kaiin_nbr and tjh.jty_nbr = tjm.jty_nbr )--and tjm.jty_msai_hyoji_sts_kbn = '07')
and tjh.KAIIN_NBR = 12012395;
select * from TM_HNKN_HOHO where SOKUJI_HNKN_FLG <> 1 and MUKO_FLG <> 1 and HNKN_HOHO_CDE <> 13;
select tjh.*,kssk.SYKKA_DTE from tt_jty_hdr tjh inner join tt_kkyak_shrai_hoho ho on ho.kkyak_shrai_hoho_id = tjh.kkyak_shrai_hoho_id and ho.shrai_hoho_kbn = '3'
inner join TT_KKYAK_SYKKA_SKN_KNRI kssk on kssk.KAIIN_NBR = tjh.KAIIN_NBR and kssk.JTY_NBR = tjh.JTY_NBR
where
exists ( select 1 from tt_jty_msai tjm where tjm.kaiin_nbr = tjh.kaiin_nbr and tjh.jty_nbr = tjm.jty_nbr and tjm.jty_msai_hyoji_sts_kbn = '09')
order by kssk.SYKKA_DTE desc;
select * from TT_MIG_JYOTO_DATA where KAIIN_NBR = 12012395;
select * from TT_KKYAK_SYKKA_SKN_KNRI where KAIIN_NBR = 12009402 and JTY_NBR = 3;
select * from TM_SMART_KAIIN_KNRI where KAIIN_NBR = '12012515';
select * from TT_MIG_JYOTO_DATA where KAIIN_NBR = '12012515';
select * from tt_jty_hdr tjh inner join tt_kkyak_shrai_hoho ho on ho.kkyak_shrai_hoho_id = tjh.kkyak_shrai_hoho_id and ho.shrai_hoho_kbn = '1' where
exists ( select 1 from tt_jty_msai tjm where tjm.kaiin_nbr = tjh.kaiin_nbr and tjh.jty_nbr = tjm.jty_nbr and tjm.jty_msai_hyoji_sts_kbn = '09');
select * from TT_SYKKA_HDR where KAIIN_NBR = 12003926 and SYKKA_KAKTE_DTE is not null;
select SYKKA_DTE from TT_KKYAK_SYKKA_SKN_KNRI where KAIIN_NBR = 12012395;
select CARD_KSYA_HNKN_SITEI_KNO_DTE from TM_SYS_CMMN;
select * from TT_MIG_JYOTO_DATA where KAIIN_NBR = '12012395';
select * from TT_AUTHRI_KNRI where KAIIN_NBR = 12012395 and kaiin_id='UN1201239500003';
select * from TM_SMART_KAIIN_KNRI where KAIIN_NBR = 12012395 and kaiin_id='UN1201239500002';
update TT_AUTHRI_KNRI set PROCESS_ID = null, PROCESS_PWD = null where KAIIN_NBR = 12012395 and JTY_NBR = 2;
select * from TT_CARD_SKN_AKDN_MSAI where KAIIN_NBR = 12012395;
#NAME?
select tjh.*, kssk.SYKKA_DTE from tt_jty_hdr tjh inner join tt_kkyak_shrai_hoho ho on ho.kkyak_shrai_hoho_id = tjh.kkyak_shrai_hoho_id and ho.shrai_hoho_kbn = '1'
inner join TT_KKYAK_SYKKA_SKN_KNRI kssk on kssk.KAIIN_NBR = tjh.KAIIN_NBR and kssk.JTY_NBR = tjh.JTY_NBR
where
exists ( select 1 from tt_jty_msai tjm where tjm.kaiin_nbr = tjh.kaiin_nbr and tjh.jty_nbr = tjm.jty_nbr and tjm.jty_msai_hyoji_sts_kbn = '09')
#NAME?
--tjh.KAIIN_NBR = 12012395 and tjh.JTY_NBR = 13
order by kssk.SYKKA_DTE desc;
select * from TM_OTAI_SYRI_KBN;
select KAIINID_SAKUJO_KIJUN_DTE, OUT_KAIINID_SAKUJO_KIJUN_DTE from TM_SYS_CMMN;
select JYOTO_ZMI_FLG from TT_AUTHRI_MSAI where KAIIN_NBR = 12012395 and JTY_NBR = 13;
select * from TT_AUTHRI_KNRI where KAIIN_NBR = 12012395 and JTY_NBR = 13;
select * from TT_KKYAK_SYKKA_SKN_KNRI where KAIIN_NBR = 12012395 and JTY_NBR = 2;
--update TT_KKYAK_SYKKA_SKN_KNRI set SYKKA_DTE = SYKKA_DTE + 30, JTY_DTE = JTY_DTE + 30,
--FNL_URAGE_DTE = FNL_URAGE_DTE + 30, SHOKAI_SEKY_DTE = SHOKAI_SEKY_DTE + 30,
--FNL_SEKY_DTE = FNL_SEKY_DTE + 30, TKSKU_KIJUN_DTE = TKSKU_KIJUN_DTE + 30,
--FNL_KESIKM_DTE = FNL_KESIKM_DTE + 30, SS_TRKU_DTM = SS_TRKU_DTM + 30, SS_KOSIN_DTM = SS_KOSIN_DTM + 30, SS_MNSI_DTE = SS_MNSI_DTE + 30
--where KAIIN_NBR = 12012376 and JTY_NBR = 8;
select * from TT_AUTHRI_KNRI where KAIIN_NBR = 12009583 and JTY_NBR = 35;
select * from TT_MIG_JYOTO_DATA where kaiin_nbr = 12012395;
select sysdate - 90 from dual;
select * from TT_CARD_SKN_AKDN_MSAI;
select * from TT_AUTHRI_KNRI where KAIIN_NBR = 12012395 and KAIIN_ID = 'UN1201239500013';
select * from TM_MDLE_KNRI where mdle_id in ('CB0092','GB0093');
select * from tt_jty_hdr tjh
inner join tt_kkyak_shrai_hoho ho on ho.KKYAK_SHRAI_HOHO_ID = tjh.KKYAK_SHRAI_HOHO_ID and ho.SHRAI_HOHO_KBN = '1' --カード
inner join TT_KKYAK_SYKKA_SKN_KNRI kssk on kssk.KAIIN_NBR = tjh.KAIIN_NBR and kssk.JTY_NBR = tjh.JTY_NBR
inner join TT_SYKKA_BTU_RYO_HSI_KNRI sbr on tjh.KAIIN_NBR = sbr.KAIIN_NBR and tjh.JTY_NBR = sbr.JTY_NBR
where (tjh.KAIIN_NBR,tjh.JTY_NBR) in (
select tjm1.KAIIN_NBR,tjm1.JTY_NBR from tt_jty_msai tjm1
inner join tt_jty_msai tjm2 on tjm1.KAIIN_NBR = tjm2.KAIIN_NBR and tjm1.JTY_NBR = tjm2.JTY_NBR and tjm1.JTY_MSAI_NBR <> tjm2.JTY_MSAI_NBR and tjm2.JTY_MSAI_HYOJI_STS_KBN = '09' and tjm2.HNPIN_STS_KBN is null and tjm1.SYKKA_JI_SYKKA_NBR = tjm2.SYKKA_JI_SYKKA_NBR
inner join tt_jty_msai tjm3 on tjm1.KAIIN_NBR = tjm3.kaiin_nbr and tjm1.JTY_NBR = tjm3.jty_nbr and tjm3.JTY_MSAI_NBR <> tjm2.JTY_MSAI_NBR and tjm3.JTY_MSAI_NBR <> tjm1.JTY_MSAI_NBR
and tjm3.JTY_MSAI_HYOJI_STS_KBN = '09'
and tjm3.HNPIN_STS_KBN is null and tjm2.SYKKA_JI_SYKKA_NBR = tjm3.SYKKA_JI_SYKKA_NBR
where tjm1.HNPIN_STS_KBN = '4'
and tjm1.JTY_MSAI_HYOJI_STS_KBN = '09'
and sbr.AZUKARKN_RYO = 0
);
#NAME?
select tjh.*, kssk.SYKKA_DTE from tt_jty_hdr tjh inner join tt_kkyak_shrai_hoho ho on ho.kkyak_shrai_hoho_id = tjh.kkyak_shrai_hoho_id and ho.shrai_hoho_kbn = '1'
inner join TT_KKYAK_SYKKA_SKN_KNRI kssk on kssk.KAIIN_NBR = tjh.KAIIN_NBR and kssk.JTY_NBR = tjh.JTY_NBR
where
exists ( select 1 from tt_jty_msai tjm where tjm.kaiin_nbr = tjh.kaiin_nbr and tjh.jty_nbr = tjm.jty_nbr and tjm.jty_msai_hyoji_sts_kbn = '09')
and
tjh.KAIIN_NBR = 12009642 and tjh.JTY_NBR = 1
order by kssk.SYKKA_DTE desc;
update TT_KKYAK_SYKKA_SKN_KNRI set SYKKA_DTE = SYKKA_DTE + 1850 where KAIIN_NBR = 41208324 and JTY_NBR = 1;
select * from TT_KKYAK_SYKKA_SKN_KNRI where KAIIN_NBR = '12009642' and JTY_NBR = 1;
select * from TT_AUTHRI_KNRI where kaiin_nbr='12009642' and jty_nbr=1;
-- don hang co 2 san pham
select kssk.SYKKA_DTE,tjh.* from tt_jty_hdr tjh
inner join tt_kkyak_shrai_hoho ho on ho.KKYAK_SHRAI_HOHO_ID = tjh.KKYAK_SHRAI_HOHO_ID and ho.SHRAI_HOHO_KBN = '1' --カード
inner join TT_KKYAK_SYKKA_SKN_KNRI kssk on kssk.KAIIN_NBR = tjh.KAIIN_NBR and kssk.JTY_NBR = tjh.JTY_NBR
inner join TT_SYKKA_BTU_RYO_HSI_KNRI sbr on tjh.KAIIN_NBR = sbr.KAIIN_NBR and tjh.JTY_NBR = sbr.JTY_NBR
where (tjh.KAIIN_NBR,tjh.JTY_NBR) in (
select tjm1.KAIIN_NBR,tjm1.JTY_NBR from tt_jty_msai tjm1
inner join tt_jty_msai tjm2 on tjm1.KAIIN_NBR = tjm2.KAIIN_NBR and tjm1.JTY_NBR = tjm2.JTY_NBR and tjm1.JTY_MSAI_NBR <> tjm2.JTY_MSAI_NBR
and tjm2.JTY_MSAI_HYOJI_STS_KBN = '09' and tjm2.HNPIN_STS_KBN is null and tjm1.SYKKA_JI_SYKKA_NBR = tjm2.SYKKA_JI_SYKKA_NBR
where tjm1.HNPIN_STS_KBN = '4'
and tjm1.JTY_MSAI_HYOJI_STS_KBN = '09'
and sbr.AZUKARKN_RYO = 0
) --and tjh.KAIIN_NBR = 12009912
and kssk.SYKKA_DTE < '2018/01/01'
order by kssk.SYKKA_DTE desc;
select * from TT_MIG_JYOTO_DATA where kaiin_nbr='12009844';
update TT_KKYAK_SYKKA_SKN_KNRI set SYKKA_DTE = SYKKA_DTE + 680 where KAIIN_NBR = 12010008 and JTY_NBR = 2;
select * from TT_KKYAK_SYKKA_SKN_KNRI where KAIIN_NBR = '12010008' and JTY_NBR = 2;
select TT_HNPIN_IRAI_HDR.* from TT_HNPIN_IRAI_HDR where KAIIN_NBR = '00000134' and JTY_NBR = 11;
select TT_HNPIN_IRAI_MSAI.* from TT_HNPIN_IRAI_MSAI where KAIIN_NBR = '00000134' and JTY_NBR = 11;
update TT_HNPIN_IRAI_HDR set HNPIN_IRAI_STS_KBN = 30 where KAIIN_NBR = '00000134' and JTY_NBR = 11;
update TT_HNPIN_IRAI_MSAI set HNPIN_IRAI_MSAI_STS_KBN = 30 where KAIIN_NBR = '00000134' and JTY_NBR = 11;
select * from TM_BTH_JKO_JOKYO_KNRI
#NAME?
order by SIJI_DTM desc;
update TM_BTH_JKO_JOKYO_KNRI set syri_jokyo = 3 where syri_jko_seq = 212912;
commit;
select * from TT_CARD_SKN_AKDN_MSAI where KAIIN_NBR = '12010009';
select * from TT_JYOTO_NYKN_ZNGK_KNRI where KAIIN_NBR = '12010009' and JTY_NBR = 7;
select * from TT_MIG_JYOTO_DATA where KAIIN_NBR='12010009' and JTY_NBR = 7;
select * from TM_SMART_KAIIN_KNRI where kaiin_nbr='12010009';
select * from TT_KKYAK_SYKKA_SKN_KNRI where KAIIN_NBR='12010009' and JTY_NBR = 7;
12012855
select * from TM_E_SCOTT_CARD_SHRAI_KBN where e_scott_card_shrai_kbn_cde='01';
select * from TM_SMART_KAIIN_KNRI;
select * from TT_OUTSOURCER_KAIIN_ID_KNRI;
select * from TT_OUTSOURCER_KAIIN_ID_KNRI;
-- don hang co 1 san pham đã được trả hàng
select kssk.SYKKA_DTE,tjh.KAIIN_NBR,tjh.jty_nbr from tt_jty_hdr tjh
inner join tt_kkyak_shrai_hoho ho on ho.KKYAK_SHRAI_HOHO_ID = tjh.KKYAK_SHRAI_HOHO_ID and ho.SHRAI_HOHO_KBN = '1' --カード
inner join TT_KKYAK_SYKKA_SKN_KNRI kssk on kssk.KAIIN_NBR = tjh.KAIIN_NBR and kssk.JTY_NBR = tjh.JTY_NBR
inner join TT_SYKKA_BTU_RYO_HSI_KNRI sbr on tjh.KAIIN_NBR = sbr.KAIIN_NBR and tjh.JTY_NBR = sbr.JTY_NBR
inner join tt_jty_msai tjm1 on tjm1.KAIIN_NBR = tjh.KAIIN_NBR and tjm1.JTY_NBR = tjh.JTY_NBR and tjm1.JTY_MSAI_HYOJI_STS_KBN = '09'
and tjm1.HNPIN_STS_KBN = '4'
where
sbr.AZUKARKN_RYO = 0
--and tjh.KAIIN_NBR = 12009912
and kssk.SYKKA_DTE > '2018/01/01'
group by kssk.SYKKA_DTE, tjh.KAIIN_NBR,tjh.jty_nbr
having count(tjh.jty_nbr) = 1
order by kssk.SYKKA_DTE desc;
-- don hang co 1 san pham trang thai
select kssk.SYKKA_DTE,tjh.KAIIN_NBR,tjh.jty_nbr from tt_jty_hdr tjh
inner join tt_kkyak_shrai_hoho ho on ho.KKYAK_SHRAI_HOHO_ID = tjh.KKYAK_SHRAI_HOHO_ID and ho.SHRAI_HOHO_KBN = '1' --カード
inner join TT_KKYAK_SYKKA_SKN_KNRI kssk on kssk.KAIIN_NBR = tjh.KAIIN_NBR and kssk.JTY_NBR = tjh.JTY_NBR
inner join TT_SYKKA_BTU_RYO_HSI_KNRI sbr on tjh.KAIIN_NBR = sbr.KAIIN_NBR and tjh.JTY_NBR = sbr.JTY_NBR
inner join tt_jty_msai tjm1 on tjm1.KAIIN_NBR = tjh.KAIIN_NBR and tjm1.JTY_NBR = tjh.JTY_NBR and tjm1.JTY_MSAI_HYOJI_STS_KBN = '09'
and tjm1.HNPIN_STS_KBN = '4'
where
sbr.AZUKARKN_RYO = 0
--and tjh.KAIIN_NBR = 12009912
and kssk.SYKKA_DTE > '2018/01/01'
group by kssk.SYKKA_DTE, tjh.KAIIN_NBR,tjh.jty_nbr
having count(tjh.jty_nbr) = 1
order by kssk.SYKKA_DTE desc;
SELECT CDE_ID, KEY_VAL, CDE_NME, KEY_NME, KEY_RYAKUSHO, MEMO, HYOJI_RNK, MUKO_FLG, MUKO_DTE
FROM TM_CDE
WHERE (CDE_ID = 'KB0229');

## PM
Module 2 - Topic 5: Writing the Project Charter
| inputs | => tools & techniques |  | => out puts
Project Charter
Module 2 - Topic 8: Identifying stakeholders
identifying stakeholders
2nd initialisation process
communications knowledge area
who, interest, influence, involvement, impact
inputs are:
- project charter
- procurement document
- enterprise environmental factors
culture and organisational structure
| stakeholders | [5 empty] | các bên liên quan
| tools & techniques | [5 empty] | công cụ & kỹ thuật
|  | - stakeholder analysis |  |  |  |  | - phân tích các bên liên quan
|  | - expert judgement |  |  |  |  | - Phán đoán chuyên môn
| stakeholders analysis | [5 empty] | phân tích các bên liên quan
|  | 1. gather who and relevant details |  |  |  |  | 1. thu thập ai và các chi tiết liên quan
|  | 2. grid influence and interest low > high |  |  |  |  | 2. ảnh hưởng lưới và lãi suất thấp> cao
|  | 3. influence to be more supportive/less negative |  |  |  |  | 3. ảnh hưởng để được hỗ trợ nhiều hơn / ít tiêu cực
| expert judgement | [5 empty] | Phán đoán chuyên môn
What are the two outputs from the Identify Stakeholder process?
Your answer: Stakeholder Register and Stakeholder Management Strategy
| Module 3 - Topic 2: Developing a project management plan | [5 empty] | Mô-đun 3 - Chủ đề 2: Xây dựng kế hoạch quản lý dự án
planning process
| why |  | why are we doing this project? |  | what is the brackground and the purpose of it?
| what |  | what are we actually building? |  | what is the work we need to do and the deliverables we need to create
| how |  | how are we going to do these things? |  |  | what policies and procedures should we be using?
| who |  | who's going to do all the work? |  |  | and for each of those people, what are their roles and their responsibilities?
| when |  | when will the work be done? |  |  | how long will each of the work activities take?
|  | input | => | T&T (techniques and tools) |  | => Output
| input: | -project charter
outputs from the other 19 processes:
- for scope, time, cost, quality,H/R, communications, risk and procurement
organisational process asset
historical information, existing PM policies and procedures, templates
enterpise environment factors
company culture and structure
infrastructure both physical and technological
resources such as people and PM software
government or industry standards
tools & techniques
expert judgement
to tailor process to suit project
to work out needed resource and skill levels
to develop the technical & management information for inclusion
decide areas that require change management
estimate how much change control management(configuration management)

## PMP
khái niệm về stakeholder:
A stakeholder is an individual, group, or organization who may affect, be affected by or perceive itself to be affected by a decision, activity, or outcome of a project. PMBOK
stakeholder là những cá nhân, tập thể, nhóm ng ảnh hưởng hoặc bị ảnh hưởng bới những quyết định, activities cho đầu ra của dự án
| baom gồm: | project team,
project sponsors
Project Manager
Portfolio Manager
Management
Other managers: functional manager, operational manager, admin manager…
Internal customer.
External Stakeholder
End user’s project outcome
A supplier
Subcontractors
Government
Local Communities
Media